## Revenue_Summary
Month | Year | Booked Orders (INR) | Invoiced Amount (INR) | Collections (INR) | Outstanding (INR) | Target Orders (INR) | Achievement (%)
January | 2026 | 18500000 | 12000000 | 10500000 | 1500000 | 20000000 | 92.5%
February | 2026 | 22000000 | 15000000 | 14000000 | 1000000 | 20000000 | 110%
March | 2026 | 38500000 | 18000000 | 17000000 | 1000000 | 25000000 | 154%
April | 2026 | 12000000 | 14000000 | 12500000 | 1500000 | 20000000 | 60%
May | 2026 | 22500000 | 16000000 | 15000000 | 1000000 | 25000000 | 90%

## Project_Status
Project Code | Project Name | Customer | Contract Value (INR) | Start Date | End Date | % Complete | Invoiced to Date (INR) | Balance to Invoice (INR) | Status | Project Manager | Delay (days) | Remarks
PRJ-NTPC-01 | 1200 TPH Conveyor System | NTPC Sipat | 38500000 | 20-Mar-2026 | 20-Mar-2027 | 12 | 4620000 | 33880000 | On Track | Channakeshava | 0 | Civil work in progress
PRJ-TATA-01 | Cement Belt System | Tata Projects | 22500000 | 02-May-2026 | 02-Nov-2026 | 5 | 1125000 | 21375000 | On Track | Vijayakumar | 0 | Drawings under approval
PRJ-NLC-01 | Coal Handling Phase 1 | NLC India | 35000000 | 01-Nov-2025 | 01-May-2026 | 95 | 33250000 | 1750000 | Delayed | Nitin | 18 | Commissioning snags
PRJ-IRCON-01 | Track Conveyor System | IRCON | 19200000 | 01-Jan-2026 | 01-Jul-2026 | 60 | 11520000 | 7680000 | On Track | Channakeshava | 0 | Structural erection done
PRJ-BHEL-01 | Fly Ash System | BHEL Trichy | 8500000 | 15-Oct-2025 | 15-Apr-2026 | 100 | 8500000 | 0 | Closed | Vijayakumar | 0 | Commissioned & handed over

## PnL_Summary
Category | Q1 FY26 (INR) | Q2 FY26 (INR) | Q3 FY26 (INR) | Q4 FY26 (INR) | FY26 Total (INR) | FY25 Total (INR) | YoY Growth (%)
Revenue | 48000000 | 52000000 | 61000000 | 73000000 | 234000000 | 180000000 | 0.3
Material Cost | 48000000 | 52000000 | 61000000 | 73000000 | 234000000 | 180000000 | 0.3
Subcontracting | 24000000 | 26000000 | 30500000 | 36500000 | 117000000 | 91000000 | 0.28571
Gross Profit | 7200000 | 7800000 | 9150000 | 10950000 | 35100000 | 27000000 | 0.3
Overheads | 16800000 | 18200000 | 21350000 | 25550000 | 81900000 | 62000000 | 0.32097
EBITDA | 9600000 | 10400000 | 12200000 | 14600000 | 46800000 | 38000000 | 0.23158
Depreciation | 7200000 | 7800000 | 9150000 | 10950000 | 35100000 | 24000000 | 0.4625
EBIT | 800000 | 800000 | 800000 | 800000 | 3200000 | 3000000 | 0.066667
Interest | 6400000 | 7000000 | 8350000 | 10150000 | 31900000 | 21000000 | 0.51905
PBT | 1200000 | 1100000 | 1050000 | 1000000 | 4350000 | 5200000 | -0.16346
| 5200000 | 5900000 | 7300000 | 9150000 | 27550000 | 15800000 | 0.74367

## OrderBook
SO Number | Customer | Segment | Order Value (INR) | Balance to Execute (INR) | Expected Completion | Priority | AM Name
SO-2026-001 | NTPC | Power | 38500000 | 33880000 | Mar-2027 | High | Umasankar
SO-2026-002 | Tata Projects | Cement | 22500000 | 21375000 | Nov-2026 | High | Vinayak
SO-2025-008 | IRCON | Railways | 19200000 | 7680000 | Jul-2026 | Medium | Jaiprakash
SO-2025-005 | NLC India | Coal | 35000000 | 1750000 | May-2026 | Low | Mohanraj
SO-2025-003 | BHEL | Power | 8500000 | 0 | Closed | Closed | Vijayakumar

## Collections
Collection ID | SO Number | Customer | Invoice No | Invoice Date | Invoice Amount (INR) | Collected Amount (INR) | Collection Date | Payment Mode | Days to Collect | Outstanding (INR)
COL-001 | SO-2026-001 | NTPC | INV-2026-012 | 01-Apr-2026 | 9625000 | 9625000 | 10-Apr-2026 | RTGS | 9 | 0
COL-002 | SO-2025-005 | NLC India | INV-2026-008 | 15-Mar-2026 | 8750000 | 8750000 | 28-Mar-2026 | RTGS | 13 | 0
COL-003 | SO-2025-008 | IRCON | INV-2026-015 | 20-Apr-2026 | 5760000 | 5760000 | 05-May-2026 | NEFT | 15 | 0
COL-004 | SO-2026-002 | Tata Projects | INV-2026-018 | 02-May-2026 | 4500000 | 0 |  | Pending | 0 | 4500000
COL-005 | SO-2025-003 | BHEL | INV-2026-005 | 01-Mar-2026 | 4250000 | 4250000 | 15-Mar-2026 | RTGS | 14 | 0

## Manpower_Summary
Department | Total Headcount | On-Site | Office | Contractor | Open Positions | Attrition YTD | Avg Experience (yrs)
Engineering | 18 | 6 | 12 | 4 | 2 | 1 | 8.5
IM Sales | 5 | 2 | 3 | 0 | 1 | 0 | 6.2
Procurement | 4 | 0 | 4 | 0 | 0 | 0 | 5.8
Projects | 12 | 10 | 2 | 8 | 3 | 2 | 9.1
Quality | 3 | 2 | 1 | 0 | 1 | 0 | 7.4
Finance & Admin | 5 | 0 | 5 | 0 | 0 | 1 | 6
Total | 47 | 20 | 27 | 12 | 7 | 4 | 7.1667